## Replatform to-do list
# | Stage | Task | Owner | Due date | Status | Comment
1 | Pre | Share staging site access with Contentsquare | You
2 | Pre | Implement your tag(s) on the staging site | You x CS |  |  | We recommend you dedicate a new tag to your staging environment, and reserve the live tag
3 | Pre | Ensure custom variables are correctly defined in the dataLayer on new site | You x CS
4 | Pre | Ensure artificial pageviews are correctly implemented on modals / pop ups | You x CS
5 | Pre | Create mappings based on the staging site's data with a clear naming convention | You |  |  | Mappings created in a staging environment can be transferred into the live project later
6 | Pre | Implement PII masking across the whole site & across API errors | You x CS
7 | Pre | Set up third party tool integrations for the new site | You x CS |  |  | E.g. analytics, AB testing, VOC tools
8 | Pre | Implement dynamic variables so we can identify replatform sessions once live | You x CS |  |  | Only relevant if new platform is being rolled out gradually
9 | Pre | Share info about how to force the replatformed site using cookies or query parameters | You |  |  | Only relevant if new platform is being rolled out gradually
10 | Pre | Zone all key pages on old site with a logical naming convention and date | You |  |  | Highly recommended but not required
11 | Pre | Export last 3 months data from page comparator | You |  |  | Recommended but not required
12 | Pre | Create workspaces & AI alerts on your key metrics (trackers below) | You
13 | Pre | Set up Speed Analysis monitors across your key pages & journeys | You
14 | Day -1 | Pre-define text strings in Text Search based on designed error pages | You |  |  | Pre-requisite: PII masking is completed
15 | Day 0 | Ensure the tag is on new site | You x CS
16 | Day 0 | Ensure your predefined mappings are populating correctly | You
17 | Day 0 | Recreate pre-existing goals & segments that are frequently used | You |  |  | Alternatively use shortcuts to quickly create segments on the fly
18 | Day 0 | Double check PII is not included in session replay | You x CS
19 | Day 0 | Zone all key pages on new site to allow for an old vs new comparison | You
20 | Day 1 | Use the error analysis module to look for costly errors | You
21 | Day 1 | Use CS Insights to review highest opportunities & identify frictions quickly | You
22 | Day 5 | Carry out a data check against you other analytics tools | You x CS |  |  | This is the recommended data collection time frame
23 | After | Use site overview and page comparator for a top level view of performance of new site | You
24 | After | Apply old and new site segments in journey analysis to compare user journeys to identify unexpected pain points | You
25 | After | Use zoning analysis to look into pages to see what elements are causing abnormal behaviour | You

## Before launch zoning list
Page | Device | Owner | Status | URL of zoning | Comment
e.g. PDP | Mobile | Nuno | FALSE
e.g. PDP | Desktop | Lisa | FALSE

## After launch zoning list
Page | Device | Owner | Status | URL of zoning | Comment
e.g. PDP | Mobile | Nuno | FALSE
e.g. PDP | Desktop | Lisa | FALSE

## To track (workspaces)
Who | Device | Page | Element | Metric | In WS? | WS Shared | Comment
e.g. Jonathan | both | pdp | Add to Cart CTA | Click Recurrence |  |  | Also to be tracked as an alert
e.g. Jonathan | both | home, pdp, plp, basket, checkout | na | Load time

## To be alerted (AI alerts)
Who | Device | Page | Element | Metric | Alert created? | Alert shared? | Comment
e.g. Jonathan | both | pdp | Add to Cart CTA | Click Recurrence |  |  | Also to be tracked in workspace

## Copy of Gantt Chart
x Replatforming launch plan
TASK NUMBER | TASK TITLE | TASK OWNER | STATUS | PRE LAUNCH | [14 empty] | DURING LAUNCH | [14 empty] | POST LAUNCH
|  |  |  | w/c/ 17 Jan |  |  |  |  | w/c 24 Jan |  |  |  |  | w/c 31 Jan |  |  |  |  | w/c 7 Feb |  |  |  |  | w/c 14 Feb |  |  |  |  | w/c 21 Feb |  |  |  |  | w/c 28 Feb |  |  |  |  | w/c 7 Mar |  |  |  |  | w/c 14 Mar
|  |  |  | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Back end re-platform
1 | Build segments for key markets | Liv B | Not started | bar: w/c/ 17 Jan F to w/c 24 Jan T
2 | Export last 3 months data from page comparator for future benchmarking |  | Not started | bar: w/c 31 Jan M to w/c 31 Jan F
3 | Build workspace tracking session-level KPIs |  | Not started
4 | Build workspace tracking page-level KPIs |  | Not started
5 | Monitor JS errors |  | Not started | bar: w/c 7 Feb M to w/c 21 Feb F
6 | Monitor workspace performance |  | Not started | bar: w/c 7 Feb M to w/c 21 Feb F
7 | Check no changes made in tag manager |  | Not started | bar: w/c 31 Jan M to w/c 14 Feb F
8 | Ensure custom & dynamic variables are correctly defined in the datalayer on new site |  | Not started | bar: w/c 31 Jan M to w/c 14 Feb F
9 | Check PIIs not included in session replay |  | Not started | bar: w/c 7 Feb M to w/c 14 Feb F
10 | Implement PII masking in checkout for SR |  | Not started | bar: w/c 28 Feb M to w/c 28 Feb F
11 | Spot check Google Optimize & Google Analytics integrations to ensure working as expected |  | Not started
12 | Set up AI Alerts to monitor site-level metrics |  | Not started | bar: w/c/ 17 Jan M to w/c/ 17 Jan F
13 | Set up AI Alerts to monitor page-level metrics |  | Not started
14 | Set up AI Alerts to monitor zone-level metrics (focus on checkout) |  | Not started | bar: w/c 31 Jan M to w/c 31 Jan F
15 | After 5 days of new site being live, carry out a data check with other analytics tools to ensure no abnormalities |  | Not started
16 | Wrap up findings & communicate with wider team |  | Not started | bar: w/c 14 Mar M to w/c 14 Mar F
Front end design changes (Apr- May)
1 | Ensure all existing key pages are zoned with a logical naming convention and date |  | Not started | bar: w/c/ 17 Jan R to w/c 24 Jan W
2 | Create mappings, goals and segments for new site elements and pages with clear naming convention |  | Not started
3 | Create snapshots of new pages to enable side by side comparison |  | Not started
4 | Compare pre/post change zonings to identify any abnormal behaviour |  | Not started | bar: w/c 14 Feb M to w/c 14 Mar F
5 | In separate tabs compare journey analysis pre/post change to spot unexpected pain points |  | Not started | bar: w/c 14 Feb M to w/c 14 Mar F
6 | Professional Services analysis (60h) |  | Not started | bar: w/c 28 Feb M to w/c 14 Mar F
7 | PS - Analysis scoping |  | Not started | bar: w/c 28 Feb M to w/c 7 Mar F
8 | PS - Delivery of analysis |  | Not started | bar: w/c 14 Mar M to w/c 14 Mar F